## List
Meeting Date | Minutes | Status
2026-03-31 | AP - 2026 03 31 | Completed
2026-04-02 | N/A | Quick updated
2026-04-10 | N/A | Quick updated
2026-04-17 | N/A | Quick updated
2026-04-23 | AP - 2026 04 23 | Completed
2026-05-07 | N/A | Quick updated
2026-05-28 | AP-2026 05 28 | Draft

## AP - 2026 03 31
CHUBB Hong Kong Limited and ACSL
Accounts Payable Meeting Minutes
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
2026-01-04 | Meeting Room No. 6 |  | 10:00 | 11:00
ATTENDEES
NAME |  | ROLE TITLE
Annie Cheung |  | Financial Controller
Cindy Chiang |  | Accounting Manager - AP
2. AGENDA
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
Kick-off meeting to set expectations and define the project scope for transforming the Accounts Payable (AP) process from Hong Kong to CCC. |  | Annie
Setup weekly meeting |  | Annie
3. PREVIOUS PROJECT MEETING REVIEW
A summary of discussions and action items from the previous meeting. Include status updates on action items from the previous meeting.
SUMMARY
N/A
ACTION ITEMS AND STATUS UPDATES |  | OWNER / PRESENTED BY | STATUS
N/A |  | Name | Complete
3. DISCUSSION POINTS
AGENDA ITEM FOR DISCUSSION |  | DISCUSSION NOTES
Transition Approach - Discussed two possible transition methods: 1) By entity (Phase 1: ACSL, followed by CHK), or 2) By PO / invoice type (Phase 1: 3-way matching suppliers, Phase 2: Subcontractors, Phase 3: Manual invoices). |  | Agreed that ACSL should be prioritized for the first phase as it has a smaller number of suppliers, making the transition more manageable. Initial scope will focus on 3-way matching invoices, followed by subcontractor invoices.
Digitalization of Procure-to-Pay (P2P) Process |  | Invoices should be received electronically rather than by post to improve processing efficiency.
Workflow Setup with CCC |  | Approval workflow should be managed via email communication instead of paper-based approval.
Payment Process |  | The payment and cash management process will remain in Hong Kong.
5. ACTION ITEMS
ACTION ITEM |  | OWNER | DUE DATE
1) Create an AP mailbox for ACSL and establish a folder structure |  | Cindy > Vicky | 2026-04-15
2) Communicate with impacted suppliers (suppliers active within the past 6 months) regarding the new invoice submission process |  | Annie | 2026-04-15
3) Prepare an approval checklist for subcontractor invoices, including identification of EC deduction requirements. |  | Cindy | 2026-04-10
4) Define the invoice posting timeline – all invoices must be posted by C1, and CCC should complete processing two days before C1. |  | Cindy | 2026-04-10
5) Establish expected KPIs for AP team members handling 3-way matching invoices, including key fields, processing timeline, and accuracy requirements |  | Cindy | 2026-04-15
6. DECISIONS MADE AND AGREED
DECISIONS
The transformation will begin with ACSL. Phase 1 scope will include 3-way matching invoices, followed by subcontractor invoices. The payment processing will remain in Hong Kong at this stage.
10. NEXT STEPS
NEXT STEPS
Confirm the detailed transition plan and timeline for the AP transformation to CCC.
11. MEETING CONCLUSION
WRAP-UP
Meeting concluded with a summary of Discussions, Action Items, and Action Holders.
DATE OF NEXT MEETING | LOCATION OF NEXT MEETING
2026-04-10 | Meeting Room No. Breakout

## AP - 2026 04 23
CHUBB Hong Kong Limited and ACSL
Accounts Payable Meeting Minutes
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
23/4/2026 | Breakout |  | 10:00 | 11:00
ATTENDEES
NAME |  | ROLE TITLE
Annie Cheung |  | Financial Controller
Cindy Chiang |  | Accounting Manager - AP
2. AGENDA
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
Update the Action Lits |  | Annie
Risk |  | Annie
3. PREVIOUS PROJECT MEETING REVIEW
A summary of discussions and action items from the previous meeting. Include status updates on action items from the previous meeting.
SUMMARY
N/A
ACTION ITEMS AND STATUS UPDATES |  | OWNER / PRESENTED BY | STATUS
N/A |  | Name | Complete
3. DISCUSSION POINTS
AGENDA ITEM FOR DISCUSSION |  | DISCUSSION NOTES
Communication with impacted suppliers |  | Supply Chain has pushed back on the communication due to unclear responsibilities. We would appreciate CCC Transformation team advice on which team is responsible for Vendor Management at HKMC. As a result, the timeframe has been extended by six weeks.
5. ACTION ITEMS
ACTION ITEM |  | OWNER | DUE DATE | Status
1) Create an AP mailbox for ACSL and establish a folder structure |  | Cindy > Vicky | 2026-04-15 | Delay
2) Communicate with impacted suppliers (suppliers active within the past 6 months) regarding the new invoice submission process |  | Annie | 2026-04-15 | Completed
3) Prepare an approval checklist for subcontractor invoices, including identification of EC deduction requirements. |  | Cindy | 2026-04-10 | Completed
4) Define the invoice posting timeline – all invoices must be posted by C1, and CCC should complete processing two days before C1. |  | Cindy | 2026-04-10 | Completed
5) Establish expected KPIs for AP team members handling 3-way matching invoices, including key fields, processing timeline, and accuracy requirements |  | Cindy | 2026-04-15 | Completed
6) Clarify which team is responsible for Vendor Management. |  | Annie | 2026-04-27
7) Test the approval checklist for subcontractor invoices, including identification of EC deduction requirements. - Pass to Vicky |  | Cindy | 2026-05-07
8) Test the nearly developed the invoice posting timeline - Pass to Nat |  | Cindy | 2026-05-07
9) Test the expected KPIs for AP team members handling 3-way matching - Pass to Ho |  | Cindy | 2026-05-07
10) Test the new AP user role for CCC - Pass to Winne and Ho |  | Cindy | 2026-04-30
6. DECISIONS MADE AND AGREED
DECISIONS
Potential risk: there may be insufficient staff to handle vendor inquiries if Vendor Management is transferred to Finance. Starting to upload invoice to JDE from May 1, 2026. Invite Ho to the meeting.
10. NEXT STEPS
NEXT STEPS
Confirm the detailed transition plan and timeline for the AP transformation to CCC.
11. MEETING CONCLUSION
WRAP-UP
Meeting concluded with a summary of Discussions, Action Items, and Action Holders.
DATE OF NEXT MEETING | LOCATION OF NEXT MEETING
2026-04-30 | Meeting Room No. Breakout

## AP - 2026 05 28
CHUBB Hong Kong Limited and ACSL
Accounts Payable Meeting Minutes
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
28/5/2026 | Breakout |  | 10:00 | 11:00
ATTENDEES
NAME |  | ROLE TITLE
Annie Cheung |  | Financial Controller
Cindy Chiang |  | Accounting Manager - AP
2. AGENDA
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
Update the Action Lits |  | Annie
Risk |  | Annie
3. PREVIOUS PROJECT MEETING REVIEW
A summary of discussions and action items from the previous meeting. Include status updates on action items from the previous meeting.
SUMMARY
N/A
ACTION ITEMS AND STATUS UPDATES |  | OWNER / PRESENTED BY | STATUS
N/A |  | Name | Complete
3. DISCUSSION POINTS
AGENDA ITEM FOR DISCUSSION |  | DISCUSSION NOTES
Communication with impacted suppliers |  | Supply Chain has pushed back on the communication due to unclear responsibilities. We would appreciate CCC Transformation team advice on which team is responsible for Vendor Management at HKMC. As a result, the timeframe has been extended by six weeks.
Transform the payment validation process to Online approval |  | Approx take six mths to clear outstanding manual invoices. Hopefully, ACSL will tickoff online approval process in Jan 2027
5. ACTION ITEMS
ACTION ITEM |  | OWNER | DUE DATE | Status
1) Create an AP mailbox for ACSL and establish a folder structure |  | Cindy > Vicky | 2026-04-15 | Completed
2) Communicate with impacted suppliers (suppliers active within the past 6 months) regarding the new invoice submission process |  | Annie | 2026-04-15 | Completed
3) Prepare an approval checklist for subcontractor invoices, including identification of EC deduction requirements. |  | Cindy | 2026-04-10 | Completed
4) Define the invoice posting timeline – all invoices must be posted by C1, and CCC should complete processing two days before C1. |  | Cindy | 2026-04-10 | Completed
5) Establish expected KPIs for AP team members handling 3-way matching invoices, including key fields, processing timeline, and accuracy requirements |  | Cindy | 2026-04-15 | Completed
6) Clarify which team is responsible for Vendor Management. |  | Annie | 2026-04-27 | Completed | Confirmed with Pele SUP team manage
7) Test the approval checklist for subcontractor invoices, including identification of EC deduction requirements. - Pass to Vicky |  | Cindy | 2026-05-07 | Completed
8) Test the nearly developed the invoice posting timeline - Pass to Nat |  | Cindy | 2026-05-07 | Completed
9) Test the expected KPIs for AP team members handling 3-way and 2-way matching - Pass to Ho |  | Cindy | 2026-05-07 | Completed
10) Test the new AP user role for CCC - Pass to Winne and Ho |  | Cindy | 2026-04-30 | Completed
11) Give AP access (CHK) to Winne and Ella. Notify Vicky |  | Cindy | 2026-06-15
12) CHK Planning transform invoice (material) input process to CCC in July |  | Cindy | 2026-06-15 |  | CCC team is not filling the KPI daily
6. DECISIONS MADE AND AGREED
DECISIONS
Potential risk: there may be insufficient staff to handle vendor inquiries if Vendor Management is transferred to Finance. Continue delay. Use workaround scan invoice manually. Delay the SubContractor invoice process.
10. NEXT STEPS
NEXT STEPS
1) Confirm the timeline for CHK 3-way invoices process in mid -July 2) Looking the InterCo process - Docuementation
11. MEETING CONCLUSION
WRAP-UP
Meeting concluded with a summary of Discussions, Action Items, and Action Holders.
DATE OF NEXT MEETING | LOCATION OF NEXT MEETING
2026-06-11 | Meeting Room No. Breakout

## Template (hidden)
CHUBB Hong Kong Limited and ACSL
Accounts Payable Meeting Minutes
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
2026-01-04 | Meeting Room No. 6 |  | 10:00 | 11:00
ATTENDEES
NAME |  | ROLE TITLE
Annie Cheung |  | Financial Controller
Cindy Chiang |  | Accounting Manager - AP
2. AGENDA
A brief outline of the topics or agenda items for the meeting.
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
The first meeting - setup our expection to transform AP process from HK to CCC. |  | N/A
3. PREVIOUS PROJECT MEETING REVIEW
A summary of discussions and action items from the previous meeting. Include status updates on action items from the previous meeting.
SUMMARY
Reviewed Meeting Minutes from the last meeting.
ACTION ITEMS AND STATUS UPDATES |  | OWNER / PRESENTED BY | STATUS
Item 1 - xxx |  | Name | Complete
4. DISCUSSION POINTS
Include a detailed discussion of each agenda item. Include key points, decisions, and information shared during the discussion. Include any presentations or visuals shared during the meeting.
AGENDA ITEM FOR DISCUSSION |  | DISCUSSION NOTES
5. ACTION ITEMS
List action items and identified during the meeting. Include responsible parties assigned to each item, due dates for each item, and note action items carried forward from previous meetings.
ACTION ITEM |  | OWNER | DUE DATE
6. DECISIONS MADE AND AGREED
Include a clear and concise description of decisions reached during the meeting. Include justifications or context for the decisions, if necessary.
DECISIONS
xxx
7. RISK MANAGEMENT
Discuss any new risks or issues identified during the meeting. Include mitigation plans to address these.
RISK OR ISSUE |  | MITIGATION PLAN
Nil
9. UPCOMING MILESTONES
Include reminders of important project milestones, deadlines, or events.
MILESTONES |  |  | DUE DATE
Nil |  |  | DD/MM/YY
10. NEXT STEPS
Summarize key next steps agreed upon in the meeting. Include any follow-up actions or tasks to be taken before the next meeting
NEXT STEPS
Confirm planning
11. MEETING CONCLUSION
Note a brief wrap-up of the meeting discussions. Confirm the date, time, and location of the next meeting. Note any materials to be distributed before the next meeting.
WRAP-UP
Meeting concluded with a summary of Discussions, Action Items, and Action Holders.
DATE OF NEXT MEETING | LOCATION OF NEXT MEETING
DD/MM/YY | Meeting Room No. 6