## List
Yes | [6 empty] | Impacted Offices | [7 empty] | PTP | AR | Sales
Ref | Priority | Confirmed Item | Item | Process Description | Team | Process Lead | MC | HK | Macau | GL | AP | AR | BU | Training | GEP | SIDETrade | Dynamics 365 | IQS | Timesheet | Status | Due Date | Comments
All | 1 | GEP | 6 | E-Invoice | AP | Cindy | Yes | Yes | Yes |  |  |  | Yes |  | Yes |  |  |  |  | On Hold | August 2025 | Pending for demo GEP system in Aug 2025
All | 2 | Phase 1 - OS | 7 | E-Approval | AP | Cindy | Yes | Yes | Yes |  |  |  | Yes |  | Yes |  |  |  |  | Completed | 2025-05-12 | Drafted the BRD, waiting for feedback before meeting with IT on May 12.
All | 3 | Phase 1 | 10 | Create New Customer Account | AR | Fan | Yes | Yes | Yes |  |  | Yes |  |  |  |  | Yes |  |  | On Hold |  | This request will be Incl. in BU process improvement
All | 4 | GEP | 8 | Payment Process (include Approval) | AP | Mona | Yes | Yes | Yes | [5 empty] | Yes |  |  |  |  | On Hold | August 2025 | Pending for demo GEP system in Aug 2025
All | 5 | BAU | 4 | Upload working file template | GL | Mona | Yes | Yes | Yes | [10 empty] | Completed | 2025-05-21 | User Guide for creating new COA and upload templates
All | 6 | BAU | 5 | COA (JDE & OneStream) | GL | Mona | Yes | Yes | Yes | [5 empty] | Yes |  |  |  |  | Completed | 2025-05-21 | User Guide for creating new COA and upload templates
Local | 7 | GEP | 9 | Late PO alert | AP | Annie |  | Yes | Yes |  | Yes |  |  |  | Yes |  |  |  |  | On Hold | August 2025 | Pending for demo GEP system in Aug 2025
All | 8 | Phase 1 | 11 | Credit Hold Review | AR | Fan | Yes | Yes | Yes |  |  | Yes |  |  |  |  | Yes | Yes |  | IQS next phase | June 2025 | Plan to improve the IQS in next Phase
Local | 9 | Phase 1 | 21 | OTC10 report preparation | Others | Eric |  | Yes | [11 empty] | Waiting for IT | 2025-05-21 | Pending approval.
All | 10 | CCC | 20 | Accounts Reconciliation and IPE | Others | Annie | Yes | Yes | Yes | [10 empty] | Completed | July 2025 | Will be starting in Q3
All | 11 | BAU | 18 | Scan document to attachment in JDE | Others | Vicky | Yes | Yes | Yes | [10 empty] | Completed | 2025-05-21 | Assessment Phase
All | 12 | Phase 1 | 15 | Credit Note | AR | Annie | Yes | Yes | Yes |  |  |  | Yes | [6 empty] | Waiting for IT | 2025-05-12 | Drafted the BRD, waiting for feedback
Local | 1a | Phase 1 | 17 | Settlement AR | Others | Annie | [13 empty] | Waiting for Approval | 2025-05-22 | Assessment Phase
Local |  | GEP | 1 | Discount Line (Purchasing) | GL | Carrie |  | Yes | Yes |  | Yes |  |  |  | Yes | [5 empty] | 2025-05-22 | Assessment the impacts
Local |  |  | 2 | On Top Journal (C2) | GL | Carrie |  | Yes |  |  | Yes | [7 empty] | Yes |  | 2025-05-22 | Assess the impacts following the implementation of a threshold limit.
Local |  |  | 3 | CAT code validation (Group Training) | GL | Carrie |  | Yes | [5 empty] | Yes
Local |  |  | 12 | Format of Statement of Account | AR | Fan |  | Yes | [7 empty] | Yes
Local |  |  | 13 | Cheque Register | AR | Vicky |  | Yes | [13 empty] | Need to explore deeply
Local |  |  | 14 | Official Receipt | AR | Mona |  |  | Yes
Local |  |  | 16 | Change the envelope cutting | General | Vicky |  | Yes | [13 empty] | Completed
Local |  |  | 19 | Service Contract Register | Others | Eric |  | ? | Yes | [12 empty] | Phase 2
|  | BAU | 21 | JDE function "Scroll to end” access | General | Vicky | Yes | Yes |  | Yes | Yes | Yes | [9 empty] | Currently, this function is not available to all roles. Team managers will assess the situation and provide details to Vicky.

## Travel Plan
|  |  |  | 550 | per night
Type | Period | No. of nights | Transportation Cost | Accommodation Cost | Meal & Misc | Total | Actual | Who | Travel Reasons
Day Trip | Sept 22 | 0 | 500 | 0 | 100 | 600 |  | Annie | Three new staff - GL team onboarding.
Overnight Trip | Sept 22 to 26 | 4 | 500 | 2200 | 1000 | 3700 |  | Carrie | Training GL team.
Overnight Trip | Sept 28 to 30 | 2 | 500 | 1100 | 600 | 2200 |  | Annie | Sox and Finance Policy Training.
Overnight Trip | Oct 09 to 11 | 2 | 500 | 1100 | 600 | 2200 |  | Carrie | Refreh Training GL team after long holiday.
Day Trip | Oct 13 (TBC) | 0 | 500 | 0 | 100 | 600 |  | Annie | Relocate from temp office to new office
Day Trip | Oct 21 (TBC) | 0 | 500 | 0 | 100 | 600 |  | Ming | Meet with the new GL team
Day Trip | Oct 28 (TBC) | 0 | 300 | 0 | 100 | 400 |  | Mona | Meet with the new GL team before the Public holiday
Overnigh Trip | Nov 10 to 14 (TBC) | 4 | 3000 | 2200 | 1000 | 6200 |  | Amy | Meet with the new GL team (SH to Macau return)
Overnight Trip | Dec 15-16 | 1 | 500 | 550 | 300 | 1350 |  | Eric | OTC09, OneStream & ReportsNow Training
Overnight Trip | Dec 15-16 | 1 | 500 | 550 | 300 | 1350 |  | Windy | OTC09, OneStream & ReportsNow Training
Day Trip | Dec 8 (TBC) | 0 | 500 | 0 | 100 | 600 |  | Annie | Monthly visit
[5 empty] | Total 2025 | 19800
Overnight Trip | Jan 13 to 15 | 2 | 500 | 1100 | 600 | 2200 |  | Annie | Review the progress, setup the KPIs and review 3 members performance
Overnight Trip | Feb 4 to 6 | 2 | 500 | 1100 | 600 | 2200 |  | Cindy | Concur training and reviewer the AP recon
Overnight Trip | Feb 5 to 6 | 1 | 500 | 550 | 600 | 1650 |  | Chi-Ho | Concur training and reviewer the AP recon
Overnight Trip | March
Overnight Trip | April
Overnight Trip | June
Overnight Trip
[5 empty] | Total 2026 | 35350

## Data
Processed Transactions
Item | Process Description | China | HK | Macau | Daily | Month
1 | Discount Line (Purchasing) | N/A | N/A | N/A
2 | On Top Journal (C2) | N/A | N/A | N/A
3 | CAT code validation (Group Training)
4 | Upload working file template | 3 files/mth x 2 entities | 3 files/mth x 3 entities | 3 files/mth x 1 entities
5 | COA (JDE & OneStream) | 3 files/mth x 2 entities | 3 files/mth x 3 entities | 3 files/mth x 1 entities
6 | E-Invoice | 3950 | 23745 | 3031 | 128.025 | 2560.5
7 | E-Approval | 1130 - OS 300 - NP | 7187 - OS 2847 - NP | 820 - OS 430 - NP |  | 694 - OS 263- NP | 761.4167 | 9137 | 5.4387
8 | Payment Process (include Approval) | 3950 | 23745 | 3031 |  |  |  |  | 3.6258
9 | Late PO alert | 3950 | 23745 | 3031
10 | Create New Customer Account | Amy | Fan | Macau
11 | Credit Hold Review | Amy | 2400 | Macau
12 | Format of Statement of Account
13 | Cheque Register |  | 32989 | 1193 | 142.425 | 2848.5
14 | Official Receipt
15 | Credit Note | 0 | 2217 | 44 | 9.4208 | 188.4167
16 | Change the envelope cutting
17 | Settlement AR | 1529 | 49071 | 1557 | 217.3208 | 4346.4167
18 | Scan document to attachment in JDE
19 | Service Contract Register
20 | Accounts Reconciliation and IPE | Jim | Carrie | Mona
21 | OTC10 report preparation |  | 658 |  |  | 164.5

## OS - Project Plan
Week Ending
Task Description | Response | Timeline | Key People | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10 | 2025-10-17
Design and Development | IT | bar: 2025-07-11 to 2025-07-25; 2025-08-15 to 2025-08-22
Functionals Testing | IT
UAT | BU |  |  | 2025-08-01: 1st UAT; 2025-09-05: 2nd UAT
| AP |  |  | 2025-08-08: 1st UAT; 2025-09-05: 2nd UAT
| Sign-Off |  |  | 2025-08-08: 2025-08-07; 2025-09-12: 2025-09-10
Qsoft | CNC |  |  | 2025-08-08: 1st Object 5.20; 2025-09-19: 2nd Object 5.70
Communication
OS |  |  | Cindy Yuen | bar: 2025-08-22 to 2025-09-05
BU Admin | bar: 2025-07-11 to 2025-07-18
PM | bar: 2025-07-18 to 2025-07-25
Approver | bar: 2025-08-08 to 2025-08-15
Finance |  |  | Cindy Chiang | bar: 2025-07-11; 2025-08-08
Documentation
Business Process |  |  | Annie | 2025-07-18: 1st Draft; 2025-08-15: 2nd Draft
Step by Step Guide |  |  | Cindy Chiang | 2025-08-01: 1st Draft; 2025-08-29: 2nd Draft
Testing Scripts
ES - Operation | Engineering
ES - Services | Project Manager
ES - S&M | Admin
CMS | Approver
FS - Operation | AP
FS - Services | OS
ES - S&M
AA
CSD
ACSL
Readiness Testing
Engineering |  |  | Annie | bar: 2025-08-01; 2025-09-05
Project Manager |  |  | Annie | bar: 2025-08-01; 2025-09-05
Admin |  |  | Annie | bar: 2025-08-01; 2025-09-05
Approver |  |  | Annie | bar: 2025-08-01; 2025-09-05
AP |  |  | Annie | bar: 2025-08-01; 2025-09-05
OS |  |  | Annie | bar: 2025-08-01; 2025-09-05

## SOX
13
Period | 2024 Q1 | 2024 Q2 | 2024 Q3 | 2024 Q4 | 2025 Q1 | 2025 Q2 | 2025 Q3 | 2025 Q4 | 2026 Q1 | 2026 Q2 | 2026 Q3 | 2026 Q4
Total Controls (incl IT) | 39 | 75 | 53 | 78 | 39 | 75 | 53 | 78 | 39 | 75 | 53 | 78
Number of Tests | 31 | 58 | 32 | 67 | 4 | 41 | 1 | 27 | 3 | 40 | 1 | 23
Reduction in Number of Tests | 8 | 17 | 21 | 11 | 35 | 34 | 52 | 51 | 36 | 35 | 52 | 55

## Progress
|  | 3 | 3 | 3 | Training Status
Lead | Job Tasks for GL Team (CCC) | 11 | 11 | 11 | Classroom | Coaching | Independent
Carrie Lam | Monthly/Quarterly/Yearly Accounts Reconciliation | 11 | 11 | 9 | 100% | 100% | 81.82%
Carrie Lam | Asset Depreciation | 3 | 3 | 2 | 100% | 100% | 66.67%
Carrie Lam | Journal Entries (Recurring) | 8 | 8 | 8 | 72.73% | 72.73% | 72.73%
Cindy Chiang | Concur Staff Claims | 1 | 1 | 1 | 33.33% | 33.33% | 33.33%
Windy Wan | Reporting OTC09 and OTC10 | 1 |  |  | 100% | 0 | 0