Minutes

China Capability Centre – MCHM Finance Team

| Date/Time | 29th April 2025, 3:00pm |
| --- | --- |
| Location | Meeting Room 4, and Online – Ms Team |
| Chairperson | Annie Cheung |
| Attendees | China - Shi, Amy (Senior Finance Manager) China - Kang, Shuzhe (Finance Control & Accounting Manager) Macau - Lok, Mona Mei Fong (Finance Manager) Hong Kong - Lau, Cheuk Ming (Finance Director) Hong Kong - Fan, Cheuk Wing (Manager - Credit Control and Collection) Hong Kong - Lam, Man Ling Carrie (Accounting Manager – GL) Hong Kong - Chiang, Cindy (Accounting Manager – AP) Hong Kong - Ng, Vicky (Secretary) Asia - Wu, Eric (Senior Manager, FP&A) |
| Apologies | N/A |
| Guests | N/A |

Project Progress Updates

| Progress Status | Number of Projects |
| --- | --- |
| Not Started | 5 |
| In Progress | 3 |
| Completed | 0 |
| On Hold | 3 |
| Awaiting review | 2 |

DISSUSSION POINTS

| Discussed Points | Description | Responsible Person |
| --- | --- | --- |
| Item 1,4 and 7 AP process improvement Status: ON HOLD | These projects will be reassessed in August 2025, following the "Source to Pay" workshops as part of the APi ExCAL program. Notes: ExCAL is a business-led program to better support our leaders and serve the business so we can reach our strategic goals and enable the success of branch and field leaders. | Item 1: Cindy + Jim Item 4: Mona + Jim Item 7: Annie + Jim |
| Item 2 Subcontractors' invoices Online Approval Workflow Status: Awaiting Review | The Business Requirements Document (BRD) has been drafted and is awaiting feedback. | Cindy + Jim |
| Item 5 and 6 Standardize COA maintenance and upload data to OneStream process Status: In Progress | Documentation is in progress, and the agreed process is being finalized between MCHM | Mona + Carrie |
| Item 9 Automatically OTC10 report preparation process Status: In Progress | Awaiting budget approval. | Eric + Pingie |
| Item 11 Create function to attach supporting document Status: Gathering Information | Waiting for team managers to provide necessary information. | Vicky + Mona |
| Item 12 Issue Credit Note process Status: Awaiting Review | The Business Requirements Document (BRD) has been drafted and is awaiting feedback. | Annie + Operation Team |
| Item 13 AR Settlement Process Status: Gathering Information | Waiting for the vendor to schedule a demonstration. Note: A demonstration was received from Chubb UK showcasing best practices for using Blackline for AR settlement | Fan + TBA |
| Item 3, 8 and 10 Create New Customer Account Credit Hold Review Standardize and Centralize process for Accounts Reconciliation and IPE Status: Not Started | Did not discuss in the meeting. | Item 3: Fan + TBA Item 8: Fan + TBA Item 10: Annie + Carrie/Jim |

ANY OTHER BUSINESS

| AOB 1 | Update the CCC Business Case (BC). - The BC was approved last week (eCAR). - Amy will continue establishing the entity in China under Shanghai entity. |
| --- | --- |
| AOB 2 | Update the relocation of Macau Office. |

Agenda for next meeting

Next meeting May 7th 2025.  Process Lead will provide an update of projects.

Meeting closed at 14:50pm