Minutes

China Capability Centre – MCHM Finance Team

| Date/Time | 7th May 2025, 10:00am |
| --- | --- |
| Location | Meeting Room 4, and Online – Ms Team |
| Chairperson | Annie Cheung |
| Attendees | China - Shi, Amy (Senior Finance Manager) China - Kang, Shuzhe (Finance Control & Accounting Manager) Hong Kong - Lau, Cheuk Ming (Finance Director) Hong Kong - Fan, Cheuk Wing (Manager - Credit Control and Collection) Hong Kong - Lam, Man Ling Carrie (Accounting Manager – GL) Hong Kong - Chiang, Cindy (Accounting Manager – AP) Hong Kong - Ng, Vicky (Secretary) Macau - Lok, Mona Mei Fong (Finance Manager) Asia - Wu, Eric (Senior Manager, FP&A) |
| Apologies | N/A |
| Guests | MCHKM – King Chau (Business Transformation Director) |

Project Progress Updates

| Progress Status | Number of Projects |
| --- | --- |
| Not Started | 5 |
| In Progress | 3 |
| Completed | 0 |
| On Hold | 3 |
| Awaiting review | 2 |

DISCUSSION POINTS

| Priority Item | Description | Status | Action Person | Due Date |
| --- | --- | --- | --- | --- |
| 1 | E-Invoice (AP process improvement) No Discussed. No further updates until August 2025. | On Hold | Cindy + Jim | - |
| 2 | Subcontractors' invoices Online Approval Workflow The Business Requirements Document (BRD) has been drafted, and Cindy will discuss with Fiona. Scheduled a meeting with the system provider on May 12. | Awaiting Review | Cindy + Jim | 12/05/25 |
| 3 | Create New Customer Account Did not discuss in the meeting. | Not Started | Fan + TBA | - |
| 4 | Payment Process include Online Approval (AP process improvement) Did not discuss in the meeting. No further updates until August 2025. | On Hold | Mona + Jim | - |
| 5 & 6 | Standardize COA maintenance and upload data to OneStream process Carrie will prepare the 1st draft (simplified version) of the User Guide which must compliance with the SOX requirement by the next meeting. Then, Mona will review and discuss with Amy. | In Progress | Mona + Carrie | 21/05/25 |
| 7 | Setup an alert process to manage Late PO when supplier invoice was issued before PO issue date AP process improvement Did not discuss in the meeting. No further updates until August 2025. | On Hold | Annie + Jim | - |
| 8 | Credit Hold Review Jason of IT will discuss with Fan after the existing changes adopt to production. | Not Started | Fan + TBA | - |
| 9 | Automatically OTC10 report preparation process eCAR has been resubmitted and awaiting budget approval. | In Progress | Eric + Pingie | 21/05/25 |
| 10 | Standardize and Centralize process for Accounts Reconciliation and IPE No Discussed. No further updates until Q3. | Not Started | Annie + Carrie/Jim | - |
| 11 | Create function to attach supporting document Team managers have provided the necessary information. Vicky will discuss with IT regarding role, function, etc. | Gathering Info | Vicky + Mona | 21/05/25 |
| 12 | Issue Credit Note process The documentation (BRD) has been done, and BU has given the feedback. Auditor concerned that there is gap between PowerApp and JDE. Annie will discuss with IT on May 12. | Awaiting Review | Annie + Ops Team | 12/05/25 |
| 13 | AR Settlement Process The demonstration of Blackline has been scheduled on May 21. Also, will schedule a demo session for JDE Settlement function with AR Finance – German. | Gathering Info | Fan + TBA | 21/05/25 |

ANY OTHER BUSINESS

| AOB 1 | Update the CCC Business Case (BC). - Amy informed that the internal approval of setting up the bank account is nearly completed. - Susan Zhou of Legal is handling the company registration in China. - No transactions are to be processed in JDE until the company registration is formally completed. |
| --- | --- |
| AOB 2 | Discount line (purchasing): Carrie will check the existing policies and discuss with Cindy Yuen the impacts. |
| AOB 3 | JDE Function “Scroll to End” Currently, this function is not available to all roles. Team managers will assess the situation and provide details to Vicky. |

Agenda for next meeting

Next meeting May 22nd 2025.  Process Lead will provide an update of projects.

Meeting closed at 11:00am