Minutes

China Capability Centre – MCHM Finance Team

| Date/Time | 2nd September 2025, 10:00am |
| --- | --- |
| Location | Meeting Room 3, and Online – Ms Team |
| Chairperson | Annie Cheung |
| Attendees | China - Kang, Shuzhe (Finance Control & Accounting Manager) China - Shi, Amy (Senior Finance Manager) Hong Kong - Ng, Vicky (Secretary) Hong Kong - Lau, Cheuk Ming (Finance Director) Hong Kong - Fan, Cheuk Wing (Manager - Credit Control and Collection) Hong Kong - Lam, Man Ling Carrie (Accounting Manager – GL) Hong Kong - Chiang, Cindy (Accounting Manager – AP) Asia - Wu, Eric (Senior Manager, FP&A) |
| Apologies | Macau - Lok, Mona Mei Fong (Finance Manager) |
| Guests | N/A |

Project Progress Updates

| Progress Status | Number of Projects |
| --- | --- |
| Not Started | 5 |
| In Progress | 2 |
| Completed | 1 |
| On Hold | 3 |
| Awaiting review | 2 |

DISCUSSION POINTS

| Priority Item | Description | Status | Action Person | Due Date |
| --- | --- | --- | --- | --- |
| 2 | Subcontractors' invoices Online Approval Workflow - The Subcontractors’ Invoices Online Approval has been launched on 1st Sep. No feedback was received from BU yet except Fiona’s team requested a training and the training will be provided on 3rd Sep. - Cindy will check with Pingie how many transactions were found. - Cindy will prepare the draft manual and walkthrough before next meeting. | In Progress (On Track) | Cindy + Jim | 16th Sep |
| 5 & 6 | Standardize COA maintenance and upload data to OneStream process The process will be formally signed off by Amy and Ming today. Carrie will follow up with Mona. | In Progress | Mona + Carrie | 5th Sep |
| 10 | Standardize and Centralize process for Accounts Reconciliation and IPE Jim will provide the updated version of the plan to Carrie by today. Vicky will schedule a meeting before 5th Sep for Jim, Carrie, Amy, Mona and Ming to discuss the access right of One Stream, JDE and Report Now for the 1st phase staff in CCC. Once the access right confirmed, a formal email will be sent by Jim/Carrie to Ming, Amy and Mona for approval. The due date for new user access should be decided and approve by next Monday 8th September. If it is a new role, IT needs to know ASAP. Carrie will upload the manual/user guide in the share drive. Vicky will implement 4 testing of accounts reconciliation (China x HK @2). | In Progress (Delay) | Annie + Carrie/Jim | 16th Sep |
| Items will be Discussed Later |  |  |  |  |
| 9 | Automatically OTC10 report preparation process Matthew has followed up with the vendor to generate data for Jobs over $1M USD. | Gathering Info | Eric + Pingie | Assessment Nov (TBC) Kick-Off (Feb 2026) |
| 11 | Create function to attach supporting document Vicky will follow up with Matthew Lo. | Gathering Info | Vicky + Mona | Parked |
| 12 | Issue Credit Note process Waiting for Vendor to revise the credit note interface. | Awaiting Review | Annie + Ops Team | Assessment Dec (TBC) Kick-Off (Mar 2026) |
| 13 | AR Settlement Process The samples for “Pool of Concepts” have been given to BlackLine already. Waiting for BlackLine to provide the quotation which includes Shanghai office. | Gathering Info | Fan + TBA | Waiting for BlackLine |
| Items on Hold / Not Started |  |  |  |  |
| 1 | E-Invoice (AP process improvement) No Discussed. No further updates until September 2025. | On Hold | Cindy + Jim | Nick in Sept |
| 3 | Create New Customer Account Did not discuss in the meeting. | Not Started | Fan + TBA | Followup with Andrew Wong |
| 4 | Payment Process include Online Approval (AP process improvement) Did not discuss in the meeting. Demo will be arranged in Sep 2025. | On Hold | Mona + Jim | Mona will continue working with HSBC ACH account fees. |
| 7 | Setup an alert process to manage Late PO when supplier invoice was issued before PO issue date AP process improvement Did not discuss in the meeting. No further updates until September 2025. | On Hold | Annie + Jim | - |
| 8 | Credit Hold Review Jason of IT will discuss with Fan after the existing changes adopt to production. | Not Started | Fan + TBA | - |

ANY OTHER BUSINESS

| AOB 1 | Update the CCC Business Case (BC). - One candidate has accepted our offer and scheduled two for the second interview this week. - Amy will share the allowance package. |
| --- | --- |
| AOB 2 | CCC Cost and Budget Allocation On charge billing structure has been confirmed. Initially consideration to sign the Service Agreement between HK, Macau and China. Mona and Ming will check the Tax requirements with the auditors. The inter-company charges will start at 1st Oct 2025. |
| AOB 3 | Due to the personnel changes in China, HK and Macau will give back up to Amy. |

Agenda for next meeting

Next meeting September 17th 2025.  Process Lead will provide an update of projects.

Meeting closed at 10:50

Meeting Minutes prepared by Vicky Ng