Minutes

China Capability Centre – MCHM Finance Team

| Date/Time | 3rd October 2025, 09:30am |
| --- | --- |
| Location | Meeting Room 4, and Online – Ms Team |
| Chairperson | Annie Cheung |
| Attendees | Hong Kong - Fan, Cheuk Wing (Manager - Credit Control and Collection) Hong Kong - Lam, Man Ling Carrie (Accounting Manager – GL) Hong Kong - Chiang, Cindy (Accounting Manager – AP) Hong Kong - Ng, Vicky (Secretary) Macau - Lok, Mona Mei Fong (Finance Manager) |
| Apologies | China - Shi, Amy (Senior Finance Manager) Hong Kong - Lau, Cheuk Ming (Finance Director) Asia - Wu, Eric (Senior Manager, FP&A) |
| Guests | N/A |

Project Progress Updates

| Progress Status | Number of Projects |
| --- | --- |
| Not Started | 4 |
| In Progress | 1 |
| Completed | 3 |
| On Hold | 3 |
| Awaiting review | 1 |

DISCUSSION POINTS

| Priority Item | Description | Status | Action Person | Due Date |
| --- | --- | --- | --- | --- |
| 10 | Standardize and Centralize process for Accounts Reconciliation and IPE Vicky has created the share folders “Account Reconciliation” under “CCC Finance Working Group (MCHM)” in Teams. Carrie has scheduled to update the list of reconciliations from 9th October daily, and Weekly report on the new joiners progress to Annie, Ming, Mona and Amy. Fan and Cindy are scheduled in Nov and Dec respectively by October 20th. Mona will review if there are any reports to be shared for reference. Annie will provide the guideline (Messages Alert Set Up.docx) to setup the notification once the file has updated. | In Progress (Delay) | Annie + Carrie |  |
| 14 | Concur Process Document the current Concur review process and payment journals: a) Cindy will prepare the first draft of the process document. b) Amy and Mona will review the process, including China and Macau, for the second draft. c) Cindy will seek final approval from Ming, Amy, and Mona. | Start | Cindy + Amy | 1st Draft October 20 2nd Draft November 3rd Final Approval November 10th |
| Items will be Discussed Later |  |  |  |  |
| 9 | Automatically OTC10 report preparation process Matthew has followed up with the vendor to generate data for Jobs over $1M USD. | Gathering Info | Eric + Pingie | Assessment Nov (TBC) Kick-Off (Feb 2026) |
| 12 | Issue Credit Note process Executives will visit UK in early Oct to explore into the global main theme of IT/System (including BlackLine and SideTrade) in the next coming years. | Awaiting Review | Annie + Ops Team | Assessment Dec (TBC) Kick-Off (Mar 2026) |
| 13 | AR Settlement Process The “Pool of Concepts” have been reviewed. The BlackLine can perform around 80% of the normal work of HK. The one-year cost of BlackLine is US$84K for HK, Macau and China. Fan will share the similar proposal from HSBC to Annie. Annie will explore any other options can be shared to HQ. | Waiting for Budget approval | Fan + TBA | Submitted for 2026 Budget approval |
| Items on Hold / Not Started |  |  |  |  |
| 1 | E-Invoice (AP process improvement) After the demonstration of the GEP AP on September 26th. It was discussed that HK will implement the GEP-AP module alongside the GEP PTP. | On Hold | Cindy |  |
| 3 | Create New Customer Account Did not discuss in the meeting. | Not Started | Fan + TBA | Followup with Andrew Wong |
| 4 | Payment Process include Online Approval (AP process improvement) ACH process was deployed in HK but the bank fee for Macau is high. | On Hold | Mona | Mona will continue working with HSBC ACH account fees. |
| 7 | Setup an alert process to manage Late PO when supplier invoice was issued before PO issue date AP process improvement After the demonstration of the GEP AP on September 26th. It was discussed that HK will implement the GEP-AP module alongside the GEP PTP. | On Hold | Annie | - |
| 8 | Credit Hold Review Jason of IT will discuss with Fan after the existing changes adopt to production. | Not Started | Fan + TBA | - |

| Items Completed |  |  |  |  |
| --- | --- | --- | --- | --- |
| 2 | Subcontractors' invoices Online Approval Workflow There are three buds to be fixed (1) Invoice Date (2) Invoice no. checking (3) outbound mailbox blocked. Annie completed the walkthrough with auditors. The samples dated after 1st Oct 2025 will be selected for testing. | Completed | Cindy |  |
| 5 & 6 | Standardize COA maintenance and upload data to OneStream process Ming, Mona and Amy have approved the process. The user guide was also shared with King Chau. | Completed | Mona + Carrie |  |
| 11 | Create function to attach supporting document Wilson informed that the function to attach the supporting document has already existed in JDE. | Completed | Vicky + Mona |  |

ANY OTHER BUSINESS

| AOB 1 | Update the CCC Business Case (BC). - China would like to move the Concur payment claim to CCC. Ho will prepare the checklist/process documentation to Mona for 1st review. |
| --- | --- |

Agenda for next meeting

Next meeting October 14th 2025.  Process Lead will provide an update of projects.

Meeting closed at 10:25

Meeting Minutes prepared by Vicky Ng