Minutes

China Capability Centre – MCHM Finance Team

| Date/Time | 14th October 2025, 03:00pm |
| --- | --- |
| Location | Meeting Room 2, and Online – Ms Team |
| Chairperson | Annie Cheung |
| Attendees | China - Shi, Amy (Senior Finance Manager) Hong Kong - Ng, Vicky (Secretary) Hong Kong - Lau, Cheuk Ming (Finance Director) Hong Kong - Lam, Man Ling Carrie (Accounting Manager – GL) Hong Kong - Chiang, Cindy (Accounting Manager – AP) Macau - Lok, Mona Mei Fong (Finance Manager) Asia - Wu, Eric (Senior Manager, FP&A) |
| Apologies | Hong Kong - Fan, Cheuk Wing (Manager - Credit Control and Collection) |
| Guests | N/A |

Project Progress Updates

| Progress Status | Number of Projects |
| --- | --- |
| Not Started | 4 |
| In Progress | 1 |
| Completed | 3 |
| On Hold | 3 |
| Start | 2 |

DISCUSSION POINTS

| Priority Item | Description | Status | Action Person | Due Date |
| --- | --- | --- | --- | --- |
| 10 | Standardize and Centralize process for Accounts Reconciliation and IPE Carrie and Mona will update the schedule list. Carrie requested to add the “quarterly” or “yearly” information into the list. Carrie will inform the CCC teammates to update the properties contents e.g. “preparer”, “reviewer” and “status” of the files and the files names must be consistent. The managers will check their works and give feedback to the CCC teammates accordingly. Carrie has given the positive comments on 3 CCC teammates. Annie requested the managers to consider assigning more works to the CCC teammates to make good use of their time. Monthly recurring journal and depreciation process will be starting from Oct. | In Progress (Delay) | Annie + Carrie | Monthly recurring journal: China and HK Nov 21–28 Macau – Dec Depreciation: China – Oct 27th Macau – Oct 27th HK – Nov 24th |
| 14 | Concur Process Cindy will provide the 1st draft of the Concur process and policies to Amy next week. Annie requested all transactions must have the receipts uploaded in the Concur starting from 1st Nov. Cindy will discuss with Mona of the final version of the process. Annie reminded that the standardized process must be approved by Amy, Mona and Ming. The training is targeted in 3rd week of Nov. | Start | Cindy + Amy | 1st Draft October 20th 2nd Draft November 3rd Final Approval November 10th |

| Items will be Discussed Later |  |  |  |  |
| --- | --- | --- | --- | --- |
| 9 | Automatically OTC10 report preparation process Annie followed up with IT that Fire Dept (HK Govt) will start to use a new form on 1st Apr 2026. IT will focus to the enhancement on it. The OTC10 will be on queue. | Gathering Info | Eric + Pingie | Assessment Nov (TBC) Kick-Off (Feb 2026) |
| 12 | Issue Credit Note process Annie discussed with IT, the Credit Note and e-Invoicing will be kicked off this quarter. Documentation has been completed. Pingie will discuss with vendor. The target go-live date is Mar 2026. | Start | Annie + Ops Team | Assessment Dec (TBC) Kick-Off (Mar 2026) |
| 13 | AR Settlement Process BlackLine, SideTrade and GEP are waiting for budget approval. | Waiting for Budget approval | Fan + TBA | Submitted for 2026 Budget approval |
| Items on Hold / Not Started |  |  |  |  |
| 1 | E-Invoice (AP process improvement) Annie will discuss with Matthew how to centralize the process this week. | On Hold | Cindy |  |
| 3 | Create New Customer Account Annie requested BU to have an on-line form in their scopes. | Not Started | Fan + TBA | Followup with Andrew Wong |
| 4 | Payment Process include Online Approval (AP process improvement) ACH process was deployed in HK but the bank fee for Macau is high. | On Hold | Mona | Mona will continue working with HSBC ACH account fees. |
| 7 | Setup an alert process to manage Late PO when supplier invoice was issued before PO issue date AP process improvement After the demonstration of the GEP AP on September 26th. It was discussed that HK will implement the GEP-AP module alongside the GEP PTP. | On Hold | Annie | - |
| 8 | Credit Hold Review This will include in the coming enhancement of IQS. | Not Started | Fan + TBA | - |
| Items Completed |  |  |  |  |
| 2 | Subcontractors' invoices Online Approval Workflow There are three buds to be fixed (1) Invoice Date (2) Invoice no. checking (3) outbound mailbox blocked. Annie completed the walkthrough with auditors. The samples dated after 1st Oct 2025 will be selected for testing. | Completed | Cindy |  |
| 5 & 6 | Standardize COA maintenance and upload data to OneStream process Ming, Mona and Amy have approved the process. The user guide was also shared with King Chau. | Completed | Mona + Carrie |  |
| 11 | Create function to attach supporting document Carrie and Cindy will provide the screenshot to Vicky for preparing the guideline for CCC. | Completed | Vicky + Mona |  |

ANY OTHER BUSINESS

| AOB 1 | Update the CCC Business Case (BC). Annie has shared the Finance Org Chart (MCHM) which includes CCC teammates. |
| --- | --- |
| AOB 12 | Agreed that the China Capability Centre – MCHM Finance Team Meeting will be hold by every three weeks. |

Agenda for next meeting

Next meeting November 4th 2025.  Process Lead will provide an update of projects.

Meeting closed at 16:05

Meeting Minutes prepared by Vicky Ng