Minutes

China Capability Centre – MCHM Finance Team

| Date/Time | 25th November 2025, 10:00am |
| --- | --- |
| Location | Meeting Room 6, and Online – Ms Team |
| Chairperson | Annie Cheung |
| Attendees | China - Shi, Amy (Senior Finance Manager) Hong Kong - Ng, Vicky (Secretary) Hong Kong - Lau, Cheuk Ming (Finance Director) Hong Kong - Lam, Man Ling Carrie (Accounting Manager – GL) Hong Kong - Chiang, Cindy (Accounting Manager – AP) Macau - Lok, Mona Mei Fong (Finance Manager) Asia - Wu, Eric (Senior Manager, FP&A) |
| Apologies | Hong Kong - Fan, Cheuk Wing (Manager - Credit Control and Collection) |
| Guests | N/A |

Project Progress Updates

| Progress Status | Number of Projects |
| --- | --- |
| Not Started | 4 |
| In Progress | 1 |
| Completed | 3 |
| On Hold | 3 |
| Start | 2 |

DISCUSSION POINTS

| Priority Item | Description | Status | Action Person | Due Date |
| --- | --- | --- | --- | --- |
| 10 | Standardize and Centralize process for Accounts Reconciliation and IPE Mona will complete the schedule list in this week. Annie recommended to remove the column “Group Account” in the schedule list. No procedures will be attached in the accounts reconciliation files and upload to OneStream. Annie also recommended to prepare a separate process documentation for Group Account. Annie emphasised that all account reconciliation files must be submitted to MCHM before Day 20th of each month and MCHM must be uploaded the files before Day 25th to OneStream. Mona, Carrie and Amy requested to have the full set reports downloaded from OneStream. Carrie will organize the OneStream training to CCC Finance staff and the invitation will be sent to China and Macau team as well. MCHM will apply for OneStream account for CCC Finance staff separately. | In Progress (Delay) | Annie + Carrie | Monthly recurring journal: China and HK Nov 21–28 Macau – Dec Depreciation: China – Oct 27th Macau – Oct 27th HK – Nov 24th |
| 14 | Concur Process Amy will review the Concur process next week. Vicky will apply the Concur account for CCC Finance staff. Annie will ask Yuri to provide the full list of China’s employees. | Start | Cindy + Amy | 1st Draft October 20th 2nd Draft November 3rd Final Approval November 10th |
| Items will be Discussed Later |  |  |  |  |
| 9 | Automatically OTC10 report preparation process Annie followed up with IT that Fire Dept (HK Govt) will start to use a new form on 1st Apr 2026. IT will focus to the enhancement on it. The OTC10 will be on queue. | Gathering Info | Eric + Pingie | Assessment Nov (TBC) Kick-Off (Feb 2026) |
| 12 | Issue Credit Note process Credit note process will be started after completion of SV process. And SideTrade system will be implemented in Q1 2026. | Start | Annie + Ops Team | Assessment Dec (TBC) Kick-Off (Mar 2026) |
| 13 | AR Settlement Process BlackLine, SideTrade and GEP are waiting for budget approval. | Waiting for Budget approval | Fan + TBA | Submitted for 2026 Budget approval |
| Items on Hold / Not Started |  |  |  |  |
| 1 | E-Invoice (AP process improvement) Annie will discuss with Matthew how to centralize the process this week. | On Hold | Cindy |  |
| 3 | Create New Customer Account Annie requested BU to have an on-line form in their scopes. | Not Started | Fan + TBA | Followup with Andrew Wong |
| 4 | Payment Process include Online Approval (AP process improvement) ACH process was deployed in HK but the bank fee for Macau is high. | On Hold | Mona | Mona will continue working with HSBC ACH account fees. |
| 7 | Setup an alert process to manage Late PO when supplier invoice was issued before PO issue date AP process improvement After the demonstration of the GEP AP on September 26th. It was discussed that HK will implement the GEP-AP module alongside the GEP PTP. | On Hold | Annie | - |
| 8 | Credit Hold Review This will include in the coming enhancement of IQS. | Not Started | Fan + TBA | - |
| Items Completed |  |  |  |  |
| 2 | Subcontractors' invoices Online Approval Workflow There are three buds to be fixed (1) Invoice Date (2) Invoice no. checking (3) outbound mailbox blocked. Annie completed the walkthrough with auditors. The samples dated after 1st Oct 2025 will be selected for testing. | Completed | Cindy |  |
| 5 & 6 | Standardize COA maintenance and upload data to OneStream process Ming, Mona and Amy have approved the process. The user guide was also shared with King Chau. | Completed | Mona + Carrie |  |
| 11 | Create function to attach supporting document Carrie and Cindy will provide the screenshot to Vicky for preparing the guideline for CCC. | Completed | Vicky + Mona |  |

ANY OTHER BUSINESS

| AOB 1 | - The Overview Finance Process Transition Plan 2025 Q4 is attached for reference. |
| --- | --- |

Agenda for next meeting

Next meeting November 25th 2025.  Process Lead will provide an update of projects.

Meeting closed at 11:20

Meeting Minutes prepared by Vicky Ng