Minutes

China Capability Centre – MCHM Finance Team

| Date/Time | 18th December 2025, 4:00pm |
| --- | --- |
| Location | Meeting Room 6, and Online – Ms Team |
| Chairperson | Annie Cheung |
| Attendees | China - Shi, Amy (Senior Finance Manager) Hong Kong - Ng, Vicky (Secretary) Hong Kong - Fan, Cheuk Wing (Manager - Credit Control and Collection) Hong Kong - Lam, Man Ling Carrie (Accounting Manager – GL) Hong Kong - Chiang, Cindy (Accounting Manager – AP) Macau - Lok, Mona Mei Fong (Finance Manager) Asia - Wu, Eric (Senior Manager, FP&A) |
| Apologies | Hong Kong - Lau, Cheuk Ming (Finance Director) |
| Guests | N/A |

Project Progress Updates

| Progress Status | Number of Projects |
| --- | --- |
| Not Started | 3 |
| On Hold | 4 |
| Start | 4 |
| Monthly Follow-up | 2 |

DISCUSSION POINTS

| Priority Item | Description | Status | Action Person | Due Date |
| --- | --- | --- | --- | --- |
| 14 | Concur Process Concur in China has totally transferred to CCC. Cindy will schedule the Part 2 meeting in Jan. Vicky will follow-up the general email address ccc_apcustomerservice@chubbfs.com. | Start | Cindy + Amy | Followup with IT |
| 15 | Journal Entries Majority of standard Journal entries of China have been handled by CCC. HK will provide training to CCC in Jan 26 for Chubb HK, ACSL, CCHL and Chubb Taiwan accounts. Adhoc Journal entries will be handled by Macau. HK’s AP voucher match of subcontractor and Non PO will be handled by Macau/CCC in Q1 2026. | Start |  |  |
| 16 | FP&A Reports (OTC09) Eric and Windy have already provided the training of ReportNow to generate the Report OCT09. CCC Finance teammates will start to generate Dec report in Jan 2026. | Start |  |  |
| Items will be Discussed Later |  |  |  |  |
| 12 | Issue Credit Note process SideTrade system will be implemented in Q1 2026. | Start | Annie + Ops Team | Assessment Dec (TBC) Kick-Off (Mar 2026) |
| 13 | AR Settlement Process BlackLine, SideTrade and GEP are waiting for budget approval. | Waiting for Budget approval | Fan + TBA | Submitted for 2026 Budget approval |
| Items On Hold / Not Started |  |  |  |  |
| 1 | E-Invoice (AP process improvement) Annie will discuss with Matthew how to centralize the process. | On Hold | Cindy |  |
| 3 | Create New Customer Account After discussion with BU, no on-line form will be implemented. Manual form will be used. CRM or JDE can be worked to setup the new customer but no SOX control. It is still under assessment. | Not Started | Fan + TBA | Followup with Jessica Yu |
| 4 | Payment Process include Online Approval (AP process improvement) ACH process was deployed in HK but the bank fee for Macau is high. | On Hold | Mona | Mona will continue working with HSBC ACH account fees. |
| 7 | Setup an alert process to manage Late PO when supplier invoice was issued before PO issue date AP process improvement After the demonstration of the GEP AP on September 26th. It was discussed that HK will implement the GEP-AP module alongside the GEP PTP. | On Hold | Annie | - |
| 8 | Credit Hold Review This will include in the coming enhancement of IQS. | Not Started | Fan + TBA | - |
| 9 | Automatically OTC10 report preparation process Annie followed up with IT that Fire Dept (HK Govt) will start to use a new form on 1st Apr 2026. IT will focus to the enhancement on it. The OTC10 will be on queue. | On Hold | Eric + Pingie |  |
| Monthly Follow-up Items |  |  |  |  |
| 2 | Subcontractors' invoices Online Approval Workflow Cindy will provide the monthly updates. | Completed | Cindy |  |
| 10 | Standardize and Centralize process for Accounts Reconciliation and IPE Carrie will provide the monthly updates. Vicky will apply the JDE role of ACSL and Chubb HK to CCC Finance teammates to generate AP and inventory reports. | Completed | Annie + Carrie |  |

ANY OTHER BUSINESS

Nil

Agenda for next meeting

Next meeting January 6th 2026.  Process Lead will provide an update of projects.

Meeting closed at 5:00pm