Minutes

China Capability Centre – MCHM Finance Team

| Date/Time | 17th April 2026, 11:00am |
| --- | --- |
| Location | Meeting Room 2, and Online – Ms Team |
| Chairperson | Annie Cheung |
| Attendees | China - Shi, Amy (Senior Finance Manager) Hong Kong - Ng, Vicky (Secretary) Hong Kong - Fan, Cheuk Wing (Manager - Credit Control and Collection) Hong Kong - Lam, Man Ling Carrie (Accounting Manager – GL) Hong Kong - Chiang, Cindy (Accounting Manager – AP) Macau - Lok, Mona Mei Fong (Finance Manager) Asia - Wu, Eric (Senior Manager, FP&A) |
| Apologies | Hong Kong - Lau, Cheuk Ming (Finance Director) |
| Guests | N/A |

Project Progress Updates

| Progress Status | Number of Projects |
| --- | --- |
| Not Started | 1 |
| On Hold | 4 |
| Start | 3 |
| Monthly Follow-up | 4 |

| Description | Completed | Planning |
| --- | --- | --- |
| - Journal Entries (Recurring) | CCHL, Taiwan, China x5 | Macau - April ACSL – April CHK - June |
| - Accounts Reconciliation | All 11 Entities |  |
| - Concur | All 6 Entities |  |
| - AP Input invoices – 3 ways match | China x5, Macau | ACSL – June (depend on Vendor Management) CHK - TBC |
| - Fixed Asset Management | China x 5 | Macau – April CHK – April ACSL – April CCHL - April |
| 6) Master Data Management - Vendor - Customer - Fixed Assets - COA - TB/OS mapping | Vendor: Macau and China x5 Fixed Assets: Macau and China x5 | Vendor: July CHK x4 Customer: Aug China x5, and HK x2 Fixed Assets: Q2 China x5 CHK x3 - May COA and others: China x5, and CHK TBC |
| 7) Dispute Management – SideTrade | N/A | 2026 Q2 |
| 8) AR Settlement System – BlackLine | N/A | 2026 Q4 |

DISCUSSION POINTS

| Priority Item | Description | Status | Action Person | Due Date |
| --- | --- | --- | --- | --- |
| 15 | Journal Entries (Recurring) The journal entries of CCHL, Taiwan Branch and China are fully handled by CCC. Most of the journal entries of Macau has been managed by CCC. Annie requested to pass the Journal entries of ACSL to CCC in Apr 2026. Carrie will inform her teammate, Phyllis, to discuss with Yannis of CCC. Phyllis reported that the standard journal entries of ACSL e.g. audited fee, maintenance fee, tax return fee, etc. have been handled by CCC in P4. She targeted that 60% & 100% journal entries of ACSL will be handled by CCC in P5 and P7 respectively. Except amortisation, it will handle by HK GL team. | In Progress | Carrie + Mona | CCHL, Taiwan Branch, China – Completed Macau – In progress ACSL: April 2026 |
| Items will be Discussed Later |  |  |  |  |
| 13 | - AR Settlement Process BlackLine confirmed to provide a new quotation for reconsideration. The system will be implemented this year and will go-live in Q4 26. The Business Case will be submitted by Annie. | Start | Fan + TBA |  |
|  | - Dispute Management Tool The kick-off meeting with SideTrade is scheduled on 17th Apr. Fan is the Project Manager and Celia is the Functional & Business Expertise. The system will be rolled out to Macau and China also. Fan will discuss the implementation plan with Mona and Amy shortly. It will go-live in Q3 26. |  |  |  |
| 1 | Suppliers/Subcontractor Invoice Submission The testing of automation has been started by ES in Apr 2026. Fire will be on hold of e-invoice. In HK, ACSL has planned to implement first. A new general email address will be created for receiving ACSL invoices. The JDE roles are created/added to the CCC teammates continuously. ACSL AP Invoice Process Transfer to CCC – Timeline: - Cindy Yuen will send an email to vendors regarding electronic invoice submission in May 2026. - Electronic invoice submission will commence on 1 June 2026. - The transfer of AP invoice processing will begin on 1 June 2026. - Hard copy invoices will not be accepted after 1 July 2026. | Start | Cindy | China – CCC Winnie – Macau (remove approve) Ella – AP role: MC, Macau (remove approve) Amy: Zoe – Trf to Ella – April 5. |
| Items On Hold / Not Started |  |  |  |  |
| 3 | Create New Customer Account / New Vendor Master / FA Capitalization After discussion with BU, no on-line form will be implemented. Manual form will be used. CRM or JDE can be worked to setup the new customer but no SOX control. It is still under assessment. Mona will handle the creation of new customer account of China in Q2 26. The creation of new vendor master and FA capitalization of HK will be proceeded by Macau in Q3 26. | On Hold | Fan + Mona | Amy – Q2 Fan - Q3 |
| 4 | Payment Process include Online Approval (AP process improvement) ACH process was deployed in HK but the bank fee for Macau is high. Cindy will discuss with Amy and will help Mona to follow up with IT. | On Hold | Mona | Mona will continue working with HSBC ACH account fees. |
| 7 | Setup an alert process to manage Late PO when supplier invoice was issued before PO issue date AP process improvement After the demonstration of the GEP AP on September 26th. It was discussed that HK will implement the GEP-AP module alongside the GEP PTP. | On Hold | Annie | - |
| 8 | Credit Hold Review This will include in the coming enhancement of IQS. | Not Started | Fan + TBA | - |
| 9 | Automatically OTC10 report preparation process Annie followed up with IT that Fire Dept (HK Govt) will start to use a new form on 1st Apr 2026. IT will focus to the enhancement on it. The OTC10 will be on queue. | On Hold | Eric + Pingie |  |
| Monthly Follow-up Items |  |  |  |  |
| 2 | Subcontractors' invoices Online Approval Workflow Cindy will provide the monthly updates. Annie updated that 20 subcontractors have been selected from each department (ES and FS) for testing. It has 50% of contractors are using this system at this stage. | Completed | Cindy |  |
| 10 | Standardize and Centralize process for Accounts Reconciliation and IPE Carrie will provide the monthly updates. Fixed Asset capitalization and depreciation of China have already handled by Macau. Carrie will discuss with Mona the plan for Chubb HK. | Completed | Annie + Carrie |  |
| 14 | Concur Process The Concur of HK, China and Macau have been fully transited to CCC. Amy confirmed with HR that China cannot use Payroll for reimbursement. Vicky will follow up the electronic filing at SharePoint. | Completed | Cindy + Amy |  |
| 16 | FP&A Reports (OTC09) Yannis of CCC has sent the emails to BU regularly and Windy will follow up with BU via TEAMS according to the status. | Completed | Eric | April 2026 |

ANY OTHER BUSINESS

Nil

Agenda for next meeting

Next meeting May 6th 2026.  Process Lead will provide an update of projects.

Meeting closed at 12:30

Meeting Minutes prepared by Vicky Ng

Appendix 1