Minutes

China Capability Centre – MCHM Finance Team

| Date/Time | 12th Jun 2026, 10:00am |
| --- | --- |
| Location | Meeting Room 5, and Online – Ms Team |
| Chairperson | Annie Cheung |
| Attendees | China - Shi, Amy (Senior Finance Manager) Hong Kong - Ng, Vicky (Secretary) Hong Kong - Fan, Cheuk Wing (Manager - Credit Control and Collection) Hong Kong - Lam, Man Ling Carrie (Accounting Manager – GL) Hong Kong - Chiang, Cindy (Accounting Manager – AP) Asia - Wu, Eric (Senior Manager, FP&A) |
| Apologies | Hong Kong - Lau, Cheuk Ming (Finance Director) Macau - Lok, Mona Mei Fong (Finance Manager) |
| Guests | N/A |

Project Progress Updates

| Progress Status | Number of Projects |
| --- | --- |
| Not Started | 1 |
| On Hold | 4 |
| Start | 3 |
| Monthly Follow-up | 4 |

| Description | Completed | Planning |
| --- | --- | --- |
| - Journal Entries (Recurring) | CCHL, Taiwan, China x5, Macau | ACSL – Targeted be completed by end-Jun including AR & Concur Chubb HK (waiting for resources) planning for Jun/Jul Action: remaining list |
| - Concur | All 6 Entities | HK & ACSL Journal – June (Ella) Payment summary – July Duplicated expenses item - Cindy |
| - AP Input invoices – 3 ways match | China x5, Macau | ACSL – June (depend on Vendor Management) CHK – early of July |
| - Fixed Asset Depreciation | China x 5 CHK ACSL CCHL Macau |  |
| 6) Master Data Management - Vendor - Customer - Fixed Assets - COA - TB/OS mapping | Vendor: Macau and China x5 Fixed Assets: Macau and China x5 | Vendor: Jun (planning) CHK x4 Customer: China x 5 - TBC HK x2 - Jun Fixed Assets: Jun Eric will discuss with Mona China x5 CHK x3 - May COA and TB/OS mapping: Macau – completed China x5 – TBC CHK - TBC ACSL – Jun Taiwan - Jun |
| 7) Dispute Management – SideTrade | N/A | Kick off – Q2 2026 Technical Workshop – Completed Functional Workshop – Completed Implementation – Early Q3 2026 |
| 8) AR Settlement System – BlackLine | N/A | To be confirmed 2026 Q4 – Macau & China |

DISCUSSION POINTS

| Priority Item | Description | Status | Action Person | Due Date |
| --- | --- | --- | --- | --- |
| 15 | Journal Entries (Recurring) Not job related JE will be handled by CCC in P5/P6. Amortisation will be handled by local GL team. | In Progress | Carrie + Mona | CCHL, Taiwan Branch, China, Macau – Completed ACSL– In progress |
| Items will be Discussed Later |  |  |  |  |
| 13 | - AR Settlement Process BlackLine confirmed to provide a new quotation for reconsideration. The system will be implemented this year and will go-live in Q4 26. The targeted commencement date is P9/P10. | Start | Fan + TBA |  |
|  | - Dispute Management Tool There is a workshop for Global IT and HK IT teams on 18th May 2026. One more demonstration of SideTrade has been arranged in the week of 11th May. It will go-live in Q3 26. |  |  |  |
| 1 | Suppliers/Subcontractor Invoice Submission ACSL AP Invoice Process Transfer to CCC – Timeline: - Cindy Yuen will send an email to vendors regarding electronic invoice submission in May 2026. - Electronic invoice submission will commence on 1 June 2026. - The transfer of AP invoice processing will begin on 1 June 2026. - Hard copy invoices will not be accepted after 1 July 2026. Ho has started to scan the invoices and attached to the JDE. Annie recommended forwarding the invoices to the general email addresses also. Vicky will follow up with IT to add the buttons which directly to ACSL/CHKL general email addresses in photocopiers. | Start | Cindy |  |
| Items On Hold / Not Started |  |  |  |  |
| 3 | Create New Customer Account / New Vendor Master / FA Capitalization The training will be provided by Maggie in May. Targeted that the Vendor Master will be fully handled by Macau before September 2026. Cindy will contact Wilson for Macau to get the access to run the full reports in ReportNow. | On Hold | Fan + Mona | Amy – Q2 Fan - Q3 |
| 4 | Payment Process include Online Approval (AP process improvement) ACH process was deployed in HK but the bank fee for Macau is high. Cindy will discuss with Amy and will help Mona to follow up with IT. | On Hold | Mona | Mona will continue working with HSBC ACH account fees. |
| 7 | Setup an alert process to manage Late PO when supplier invoice was issued before PO issue date AP process improvement After the demonstration of the GEP AP on September 26th. It was discussed that HK will implement the GEP-AP module alongside the GEP PTP. | On Hold | Annie | - |
| 8 | Credit Hold Review (IQS) This will include in the coming enhancement of IQS. Fan will check with Polly of IT. It will commence in Q2 or Q3. | Not Started | Fan + TBA | - |
| 9 | Automatically OTC10 report preparation process Annie followed up with IT that Fire Dept (HK Govt) will start to use a new form on 1st Apr 2026. IT will focus to the enhancement on it. The OTC10 will be on queue. | On Hold | Eric + Pingie |  |
| Monthly Follow-up Items |  |  |  |  |
| 2 | Subcontractors' invoices Online Approval Workflow Cindy will provide the monthly updates. Annie updated that 20 subcontractors have been selected from each department (ES and FS) for testing. It has 50% of contractors are using this system at this stage. | Completed | Cindy |  |
| 10 | Standardize and Centralize process for Accounts Reconciliation and IPE Carrie will provide the monthly updates. Fixed Asset capitalization and depreciation of China have already handled by Macau. Carrie will discuss with Mona the plan for Chubb HK. | Completed | Annie + Carrie |  |
| 14 | Concur Process The Concur of HK, China and Macau have been fully transited to CCC. Amy confirmed with HR that China cannot use Payroll for reimbursement. Vicky will follow up the electronic filing at SharePoint. | Completed | Cindy + Amy |  |
| 16 | FP&A Reports (OTC09) Yannis of CCC has sent the emails to BU regularly and Windy will follow up with BU via TEAMS according to the status. | Completed | Eric | April 2026 |

ANY OTHER BUSINESS

Nil

Agenda for next meeting

Next meeting Jun 26th 2026.  Process Lead will provide an update of projects.

Meeting closed at 11:00

Meeting Minutes prepared by Vicky Ng